## Autonomous RC Car with IMU-Enhanced Autonomy

Project Management Plan & Closing Documentation

Project Title: Autonomous RC Car with IMU-Enhanced Features

Course: HBAI 42001 / PJMT 41000 – AI Capstone / Project Management Final Project

Instructor: Mohammad Shamas

Team Members: Nicolas Maitland, Christopher Kenedi

Project Management Final Project Presentation: December 2, 2025

Project Management Final Project Submitted: December 5, 2025

Project Start Date: January 12, 2026

Planned Presentation Week: Week of April 20, 2026

## 1. Updated Project Charter & Scope Statement

### 1.1 Project Background

For the Spatial Analysis final project, the team proposed an autonomous 1/18-scale Latrax Rally RC car powered by an NVIDIA Jetson Nano and an Intel RealSense D435i depth camera, implementing lane following, obstacle avoidance, and basic object detection on-board.

The current AI project extends that work by:

- Fully adopting the RealSense D435i (RGB-D + IMU) in addition to the depth camera.

- Adding IMU-driven features such as:

  - Drift detection and stability control

  - IMU-based steering smoothing

  - Crash/rollover detection and safe stop

  - Incline/terrain awareness integrated with depth perception

This project is sized to be realistic for implementation in the HBAI 42001 Capstone.

### 1.2 Project Purpose & Justification

Purpose:

Design, implement, and demonstrate an edge-deployed AI system that allows a small RC car to navigate autonomously using onboard perception (RGB-D + IMU) and lightweight deep learning models.

Justification:

- Applies AI, edge computing, and MLOps concepts on real hardware.

- Provides a reusable platform for future capstone iterations and experiments.

- Demonstrates full project lifecycle management in line with PMI process groups (initiating through closing). (Project Management Institute, 2017, 2022)

### 1.3 Measurable Project Objectives

By the week of April 20, 2026, the project will:

- Autonomous navigation:

  - Car completes at least 3 consecutive laps of a taped indoor track (≥ 3 m x 3 m, with curves) with no collisions and no manual steering intervention.

- Obstacle avoidance:

  - Car detects a static obstacle in its lane and either stops ≥ 20 cm before impact OR navigates around it at least 3/3 trials.

- IMU-enhanced features:

  - Drift detection/stability control prevents spin-out on at least 80% of aggressive turn tests.

  - Crash/rollover detection cuts throttle within ≤ 0.1 s of detection, in 100% test cases.

- MLOps & deployment:

  - Models deployed on Jetson Nano in a Dockerized environment with at least:

    - 1 REST API endpoint for inference, and

    - 1 Streamlit interface for monitoring/demo.

- Documentation & presentation:

  - All required project management deliverables completed (charter, plan, risk register, status reports, QA records, closure).

  - 15–20 minute in-person demo and presentation delivered in the week of April 20, 2026.

### 1.4 High-Level Requirements

Functional Requirements

- Lane following on an indoor taped track using RGB or RGB-D input.

- Obstacle detection and safe response (stop or avoid).

- RealSense D435i depth integration in the inference pipeline.

- IMU-based features:

  - Drift detection and corrective steering

  - IMU-aided steering smoothing

  - Crash/rollover detection and safe stop

  - Incline awareness and throttle adjustment

- Edge deployment on Jetson Nano with real-time or near real-time performance (≥ 10 Hz control loop).

- Streamlit UI to visualize sensor feeds, predictions, and system state.

Non-Functional Requirements

- Inference latency low enough for safe control (user target ≤ 100 ms end-to-end).

- System stability during 10–15 minute continuous demo.

- Code versioned in Git with reproducible setup (README + Dockerfile).

### 1.5 Assumptions & Constraints

Assumptions

- Jetson Nano, Latrax Rally chassis, RealSense D435i, and TP-Link TL-WN725N are available and functional.

- Access to lab space for track setup and testing at least 2–3 times per week.

- Cloud or lab GPU access available for model training.

- Instructor approves this topic as acceptable for capstone implementation.

Constraints

- Project duration limited to Jan 12 – presentation week of Apr 20, 2026 (~15 weeks).

- Team size fixed at two students.

- Budget limited (student project; hardware reuse strongly preferred).

- Academic deadlines and other course loads may limit available hours.

### 1.6 High-Level Risks (charter level)

- Hardware failure or long lead times for replacement.

- RealSense IMU integration more complex than expected.

- Edge performance insufficient for real-time control.

- Team availability issues (illness, exams, job interviews).

- Scope creep (too many features; not enough time).

(Full risk register in Section 3.)

### 1.7 Major Milestones

| Mile-stone ID | Milestone | Target Date |
| --- | --- | --- |
| M1 | Project charter & scope approved | Jan 26, ‘26 |
| M2 | Detailed project plan & risk register baseline | Feb 2, ‘26 |
| M3 | Hardware assembled & base lane-following model running on Nano | Mar 2, ‘26 |
| M4 | IMU-enhanced features integrated (stability, crash detect, incline) | Mr 23, ‘26 |
| M5 | System integration & full test track demo (beta) | Apr 6, ‘26 |
| M6 | Final documentation & presentation ready | Apr 20, ‘26 |

### 1.8 Key Stakeholders & Roles

- Project Sponsor / Course Instructor: approves scope, evaluates final deliverables.

- Project Manager (Student 1): overall planning, schedule, risk, communication.

- Technical Lead (Student 2): architecture, ML models, integration, performance.

- Capstone Committee / Peers: secondary stakeholders, demo audience.

### 1.9 Scope Statement

In Scope

- Autonomous driving on a fixed indoor track.

- Camera-based and depth-based perception using RealSense D435i.

- IMU-driven control features as defined in IMU integration plan.

- Model training on recorded driving data.

- Edge deployment, Dockerization, API + Streamlit UI.

Out of Scope

- Outdoor driving or high-speed racing.

- Full SLAM, global mapping, or multi-vehicle coordination.

- Advanced path planning beyond local lane following and simple reactive avoidance.

- Commercial-grade safety certification.

Acceptance Criteria (at closing)

- All measurable objectives in Section 1.3 met or clearly justified if not.

- Live demo successfully completed in front of class.

- All required documents delivered in final submission.

## 2. Detailed Project Plan (Schedule, Budget, Resources)

### 2.1 Work Breakdown Structure (WBS)

Level-1 WBS

- Project Initiation

- Project Planning

- Data & Model Development

- IMU Integration & New Autonomous Features

- System Integration, Testing & Demo Prep

- Closing & Presentation

Level-2/3 WBS

1.0 Project Initiation

- 1.1 Review prior Spatial Analysis proposal and project plan

- 1.2 Identify stakeholders & project sponsor

- 1.3 Draft and approve project charter

2.0 Project Planning

- 2.1 Refine detailed functional & non-functional requirements

- 2.2 Create WBS and schedule baseline

- 2.3 Estimate costs and define budget baseline

- 2.4 Develop risk management plan and risk register

- 2.5 Define communications & quality management plans

3.0 Data & Model Development

- 3.1 Set up Git repo, environment, and data logging pipeline

- 3.2 Design and set up physical track

- 3.3 Collect labeled driving data (manual teleop sessions)

- 3.4 Train and validate lane-following model

- 3.5 Train obstacle detection / sign detection model

- 3.6 Package models for deployment (ONNX/TensorRT)

4.0 IMU Integration & New Autonomous Features

- 4.1 Implement IMU-based drift detection & stability control

- 4.2 Implement IMU-aided steering smoothing

- 4.3 Implement crash/rollover detection and emergency stop

- 4.4 Implement incline awareness and throttle control

5.0 System Integration, Testing & Demo Prep

- 5.1 Hardware integration (Jetson + RealSense + RC car + Wi-Fi)

- 5.2 Real-time inference pipeline and control loop

- 5.3 Streamlit dashboard & REST API endpoints

- 5.4 System testing (functional, performance, safety)

- 5.5 Demo scenario design and rehearsal

6.0 Closing & Presentation

- 6.1 Final documentation (technical + PM artifacts)

- 6.2 In-class presentation and live demo

- 6.3 Lessons-learned workshop

- 6.4 Formal closure and repository handoff

### 2.2 Schedule & Timeline (Baseline)

Project duration: Jan 12 – week of Apr 20, 2026 (~15 weeks).

#### 2.2.1 High-Level Schedule Table

| ID | Task | Start | Finish | Duration (weeks) | Primary Owner |
| --- | --- | --- | --- | --- | --- |
| 1.0 | Initiation | Jan 12 | Jan 25 | 2 | PM |
| 2.0 | Planning | Jan 19 | Feb 2 | 2 | PM |
| 3.0 | Data & Model Development | Feb 2 | Mar 9 | 5 | Tech Lead |
| 4.0 | IMU Integration & New Features | Feb 23 | Mar 30 | 5 | Tech Lead |
| 5.0 | Integration, Testing & Demo Prep | Mar 2 | Apr 13 | 6 | Both |
| 6.0 | Closing & Presentation | Apr 6 | Apr 24 | 3 | PM |

#### 2.2.2 Gantt-Style Visualization (Weeks 1–15)

Legend: █ = active weeks (approximate)

| Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.0 Initiation | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.0 Planning |  | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.0 Data & Model Dev |  |  | █ | █ | █ | █ | █ |  |  |  |  |  |  |  |  |
| 4.0 IMU Integration |  |  |  |  | █ | █ | █ | █ | █ |  |  |  |  |  |  |
| 5.0 Integration & Testing |  |  |  |  |  | █ | █ | █ | █ | █ | █ |  |  |  |  |
| 6.0 Closing & Presentation |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ |

### This schedule becomes the schedule baseline; progress will be tracked against it in status reports and during monitoring & controlling. (Project Management Institute, 2017)

### 2.3 Resource Plan

#### 2.3.1 Human Resources

| Role | Responsibility Highlights | Est. Effort (hrs) |
| --- | --- | --- |
| Project Manager | Charter, plan, risk, comms, schedule, closure | 70 |
| Technical Lead | Models, IMU features, integration, performance tuning | 90 |
| Both (pair) | Data collection, testing, documentation, presentation | 80 (shared) |
| Sponsor / Instructor | Approvals, feedback, evaluation | n/a (oversight) |

Total estimated student effort: ~240 hours over the term.

#### 2.3.2 Physical / Technical Resources

- Hardware:

  - Latrax Rally 1/18-scale RC car (platform).

  - NVIDIA Jetson Nano (4 GB) with power supply.

  - Intel RealSense D435i depth camera with IMU.

  - TP-Link TL-WN725N Wi-Fi USB adapter.

  - Batteries, charger, cabling, mounting hardware.

- Software:

  - Ubuntu / JetPack on Jetson Nano.

  - PyTorch, TensorRT, RealSense SDK, OpenCV.

  - GitHub repository, VS Code / IDE, Streamlit.

- Facilities:

  - Lab/room space for track and demo.

  - Access to GPU machine or cloud credits for training.

#### 2.3.3 RACI Visualization (sample for key activities)

| Activity | Sponsor | PM | Tech Lead | Capstone Committee |
| --- | --- | --- | --- | --- |
| Approve charter & scope | A | R | C | I |
| Define detailed technical scope | C | R | R | I |
| Train and optimize models | I | C | R | I |
| Implement IMU features | I | C | R | I |
| Prepare and deliver presentation | A | R | R | C |

R = Responsible, A = Accountable, C = Consulted, I = Informed (Verzuh, 2011)

### 2.4 Budget & Cost Baseline (Approximate, for academic planning)

### Because this is a student project, much hardware is already be owned or borrowed; however, a notional budget is defined as the cost baseline. (Project Management Institute, 2017)

| Cost Item | Qty | Est. Unit Cost (USD) | Est. Total |
| --- | --- | --- | --- |
| Latrax Rally RC car chassis | 1 | $140 | $140 |
| NVIDIA Jetson Nano 4 GB dev kit | 1 | $150 | $150 |
| Intel RealSense D435i depth camera | 1 | $200 | $200 |
| TP-Link TL-WN725N Wi-Fi adapter | 1 | $10 | $10 |
| Misc. hardware (mounts, wiring, PLA, tape) | 1 | $50 | $50 |
| Misc. cloud compute / GPU credits | 1 | $50 | $50 |
| Total Direct Cost (reference) |  |  | $600 |

Labor cost for students is assumed $0 (unpaid coursework). For project management purposes we still estimate hours (Section 2.3) and could assign a hypothetical labor rate if required for EVM exercises.

This table, together with the WBS and schedule, forms the scope–schedule–cost baseline for monitoring and control (Project Management Institute, 2017, 2022).

### 2.5 Performance Measurement Approach

### Following PMBOK guidance, the project will use the baselines above to measure performance (Project Management Institute, 2017):

- Scope baseline: WBS + defined deliverables in Sections 1 & 2.

- Schedule baseline: Gantt in Section 2.2.

- Cost baseline: Budget in Section 2.4.

Monitoring/control will be via:

- Percent complete per WBS work package (updated weekly).

- Simple traffic-light indicators (Green/Yellow/Red) per knowledge area in status reports.

- Optional: basic Earned Value metrics (EV, PV, AC) for major phases (Initiation, Planning, Execution, Closing) as needed.

## 3. Risk Management Plan (Updated Risk Register)

### 3.1 Risk Management Approach

The team will follow PMI’s risk management process: plan, identify, perform qualitative analysis, plan responses, and monitor/control risks (Project Management Institute, 2017, 2022). Risks will be reviewed in weekly check-ins.

### 3.2 Risk Probability–Impact Matrix (Visualization)

Scale: 1 = Very Low, 5 = Very High

| Impact \ Probability | 1 Very Low | 2 Low | 3 Medium | 4 High | 5 Very High |
| --- | --- | --- | --- | --- | --- |
| 5 Very High |  |  | R3 | R1 |  |
| 4 High |  | R7 | R4 | R2 |  |
| 3 Medium |  |  | R5 |  |  |
| 2 Low | R9 | R8 |  |  |  |
| 1 Very Low | R6 |  |  |  |  |

(See risk register below for IDs.)

### 3.3 Risk Register

| ID | Risk Description | Category | Prob (1–5) | Impact (1–5) | Score | Response Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | RealSense D435i or Jetson Nano hardware failure close to demo | Technical | 3 | 5 | 15 | Mitigate / Plan – Handle carefully; stress-test early; keep backup camera/RC car where possible; lock down hardware changes 2 weeks pre-demo. | Tech Lead |
| R2 | IMU integration more complex than expected; IMU features not stable | Technical | 4 | 4 | 16 | Mitigate – Phase IMU features; deliver basic crash detect first; treat advanced drift control as stretch; keep simple depth-only safety stop as backup. | Tech Lead |
| R3 | Real-time performance on Jetson insufficient for safe driving | Technical | 3 | 5 | 15 | Mitigate – Use lightweight models, TensorRT, reduce resolution; if needed, fall back to simpler rule-based control for some features. | Tech Lead |
| R4 | Training data insufficient or low quality → poor model performance | Technical | 3 | 4 | 12 | Mitigate – Schedule multiple data collection sessions; use augmentation; gather failure cases and retrain. | Both |
| R5 | Team time conflicts (midterms, interviews) | Human | 3 | 3 | 9 | Mitigate – Front-load critical tasks; maintain shared task board; schedule around known busy weeks. | PM |
| R6 | Scope creep (too many features, e.g., adding object tracking mode) | Scope | 2 | 3 | 6 | Avoid – Enforce scope freeze at end of Planning; treat extra features as optional stretch goals only after baseline is working. | PM |
| R7 | Lab space unavailable during key testing weeks | External | 2 | 4 | 8 | Mitigate – Reserve room early; identify backup space; design track that can be temporarily set up in hall if needed. | PM |
| R8 | Git / Docker issues on Jetson causing environment drift | Process | 2 | 2 | 4 | Mitigate – Document setup thoroughly; test Docker build early; tag stable commits before major changes. | Tech Lead |
| R9 | Demo day nerves / system fails in front of class | Reputation | 2 | 2 | 4 | Mitigate / Accept – Rehearse multiple times; prepare “Plan B” video demo and slides; ensure manual override and emergency stop. | Both |

### 3.4 Risk Response Summary

- Mitigation actions are embedded in the schedule (e.g., early hardware integration, dedicated data collection sprints).

- Risk monitoring done weekly; new risks or changed ratings are logged in status reports.

- Escalation: any risk with Score ≥ 12 discussed explicitly with instructor for guidance.

## 4. Project Execution Documentation (Simulated)

Below are sample execution artifacts as if the project is being/has been managed across the term, in line with PMI’s Executing and Monitoring/Controlling process groups (Project Management Institute, 2017, 2022).

### 4.1 Execution & Monitoring Approach

- Follow high-level waterfall structure (Initiate → Plan → Execute → Close) with iterative build–test cycles (mini-sprints) for model and feature development. (Verzuh, 2011)

- Weekly stand-up/check-in meetings (30–45 minutes).

- Status reports every 2–3 weeks to track scope, schedule, cost, risks.

- Change control lite: any scope change affecting dates or demo complexity is logged and explicitly approved by both team members and, if needed, instructor.

### 4.2 Sample Status Reports (Progress Reports)

#### Status Report #1 – Week 3 (Jan 26 – Feb 1, 2026)

Overall Status: Green

Scope

- Charter approved; project scope aligned with Autonomous RC Car Plan and IMU extensions.

- Confirmed core features vs. stretch goals.

Schedule

- On track with Initiation & Planning milestones (M1 & M2).

- WBS and schedule baseline drafted; risk register v1 created.

Cost

- No actual costs beyond existing hardware. Cost baseline documented (approx. $600).

Completed This Period

- Reviewed previous Spatial Analysis proposal and clarified AI capstone fit.

- Drafted project charter & scope; obtained instructor sign-off.

- Built initial WBS and high-level Gantt.

Next Period

- Finalize detailed requirements (lane following, obstacle behaviors, IMU features).

- Set up Git repo and development environment on Jetson.

Issues / Risks

- R2: IMU integration complexity – flagged for early attention.

- No schedule or cost variances at this stage.

#### Status Report #2 – Week 8 (Mar 2 – Mar 8, 2026)

Overall Status: Yellow (performance risk)

Scope

- Core scope unchanged.

- Object tracking mode officially declared stretch goal only.

Schedule

- Lane-following model trained and deployed on Jetson; car can follow track at low speed. (M3 met)

- IMU features 4.1–4.4 partially implemented; behind original internal target by ~1 week.

Cost

- Additional $30 spent on replacement mounting hardware.

- Still within notional $600 budget baseline.

Completed This Period

- Data collection runs completed on indoor track.

- Lane-following CNN trained; early testing shows stable behavior.

- RealSense D435i depth streaming integrated into control loop.

Next Period

- Tune TensorRT optimization to reach ≥ 10 Hz control loop.

- Finish IMU drift detection and crash detection; begin incline awareness logic.

- Start integration of Streamlit dashboard.

Issues / Risks

- Risk R3 (performance): YOLO-based obstacle detection slower than expected; exploring model size reduction / lower resolution.

- Risk R2 (IMU complexity) remains medium–high; mitigation: reduce ambitions for advanced drift control if schedule pressure increases.

#### Status Report #3 – Week 13 (Apr 6 – Apr 12, 2026)

Overall Status: Green

Scope

- All core features implemented: lane following, obstacle stop, IMU crash detection, incline awareness.

Schedule

- Completed full system test and demo rehearsal – M5 achieved.

- On track for final presentation in week of April 20.

Cost

- No further purchases; total actual ≈ baseline.

Completed This Period

- Integrated IMU drift detection and steering smoothing; improved turn stability.

- Implemented crash/rollover detection: verified throttle cut within ≤ 0.1 s in tests.

- Implemented Streamlit dashboard visualizing camera feed, IMU status, and controls.

- Demo script drafted; full rehearsal completed.

Next Period

- Final fine-tuning, documentation polishing, and slide creation.

- Backup video recording of successful runs for contingency.

Issues / Risks

- Minor: lab availability for final rehearsal; addressed via early booking (mitigation for R7).

- No open critical risks.

### 4.3 Quality Management & QA Records

#### 4.3.1 Quality Approach

- Define acceptance tests linked to measurable objectives (Section 1.3).

- For each feature, define test cases with expected results.

- Track defects and re-test after fixes. (Project Management Institute, 2017; Verzuh, 2011)

#### 4.3.2 Test Coverage Matrix (Visualization)

| Feature / Objective | T1 | T2 | T3 | T4 | T5 | T6 |
| --- | --- | --- | --- | --- | --- | --- |
| Lane following – 3 laps, no collisions | X | X |  |  |  |  |
| Obstacle detection – safe stop/avoidance |  | X | X |  |  |  |
| IMU drift detection & stability |  |  | X | X |  |  |
| Crash/rollover detect & safe stop |  |  |  | X | X |  |
| Incline awareness & throttle control |  |  |  |  | X | X |

#### 4.3.3 Sample QA Test Log

| Test ID | Description | Expected Result | Actual Result (simulated) | Status | Date |
| --- | --- | --- | --- | --- | --- |
| T1 | Car follows simple oval track, 1 lap | Completes lap without leaving lane | Success; minor steering oscillation at turn | Pass | Mar 5, 2026 |
| T2 | Car follows track for 3 consecutive laps | 3 laps, no collisions or manual intervention | Success in 3/3 trials | Pass | Mar 20, 2026 |
| T3 | Sudden aggressive turn on smooth floor | IMU drift control triggers, car does not spin | Yaw spike detected, counter-steer applied; no spin | Pass | Mar 25, 2026 |
| T4 | Manual tip-over of car | System detects rollover, cuts throttle ≤ 0.1 s | Throttle cut in ~0.06 s (timed), log created | Pass | Mar 28, 2026 |
| T5 | Downhill segment of small ramp | System reduces throttle, maintains safe speed | Speed increase limited; no runaway behavior | Pass | Apr 2, 2026 |
| T6 | Obstacle placed mid-lane on straight | Car stops ≥ 20 cm before obstacle | Stopped ~25 cm away in 3/3 trials | Pass | Apr 4, 2026 |

### 4.4 Change Log

| Change ID | Description | Type | Impact on Scope/Schedule | Approved By | Date |
| --- | --- | --- | --- | --- | --- |
| C-01 | Demote object tracking mode to stretch goal | Scope down | Reduced risk to schedule | Team + Instructor | Feb 10, 2026 |
| C-02 | Replace planned detour behavior with safe stop only for obstacles (if needed) | Scope adjust | Simplifies integration; ensures reliability | Team | Mar 8, 2026 |

## 5. Lessons Learned Report & Project Closure

### 5.1 Lessons Learned (by Knowledge Area)

Scope & Requirements

- Clear early separation between must-have and stretch features (e.g., object tracking) prevented scope creep and made it easier to de-scope when schedule risk appeared. (Project Management Institute, 2022; Verzuh, 2011)

- Using the previous project plan and IMU extension documents as structured technical scope references reduced ambiguity.

Schedule & Estimation

- IMU integration tasks (4.1–4.4) took longer than initial estimates; they involved more tuning and testing than pure coding. Future projects should allocate more slack for integration work.

- Early completion of hardware setup (M3 by March 2) was critical; it allowed significant time for iteration, aligning with best practice of minimizing late technical surprises (Verzuh, 2011).

Technical & Quality

- Combining RealSense depth with IMU improved robustness, particularly for slope and crash detection, validating the design assumption that sensor fusion adds value beyond camera alone.

- Real-time constraints on Jetson required careful optimization; designing with lightweight models from the beginning reduced rework.

Risk & Issue Management

- The formal risk register helped the team identify R2 (IMU complexity) and R3 (performance) early and adjust scope and technical approach accordingly.

- Explicit mitigation plans (e.g., safe stop instead of detour) made decisions easier when schedule pressure increased.

Teamwork & Communication

- Weekly stand-ups plus mid-week async updates kept both team members aligned.

- A simple shared Kanban board (To-Do / Doing / Done) mapped to WBS items aided transparency and self-assignment of work.

Tools & MLOps

- Maintaining a clean Git history and tagging “demo-stable” releases simplified rollback when new changes broke something.

- Dockerization ensured the Jetson environment matched the development environment, reducing “works on my machine” issues.

### 5.2 Project Closure Checklist

| Item | Status |
| --- | --- |
| All planned features implemented or formally de-scoped | ✓ |
| All acceptance tests executed (Section 4.3) | ✓ |
| Final code pushed to main branch with tag “v1.0” | ✓ |
| Docker image built and tested on Jetson | ✓ |
| Streamlit dashboard and REST API documented | ✓ |
| Project management deliverables (this document, risk register, status reports, QA log) submitted | ✓ |
| Final presentation & live demo delivered | ✓ |
| Lessons learned documented and discussed with instructor | ✓ |

### 5.3 Formal Acceptance & Sign-Off (Template)

Project Sponsor / Instructor:

I acknowledge that the Autonomous RC Car with IMU-Enhanced Autonomy project has met the agreed-upon objectives and acceptance criteria, or that any deviations have been clearly documented and justified.

Name: _____________________________

Signature: ________________________

Date: _____________________________

## 6. References (APA 7th)

Project Management Institute. (2017). A guide to the project management body of knowledge (PMBOK® guide) (6th ed.). Newtown Square, PA: Project Management Institute.

Project Management Institute. (2022). Process groups: A practice guide. Newtown Square, PA: Project Management Institute.

Verzuh, E. (2011). The fast forward MBA in project management (4th ed.). Hoboken, NJ: John Wiley & Sons.